## Overview
AI project workbook
Benian Technologies. Version 2.0. Published September 7, 2026.
Project | Enter your project in Project brief
Start here
1. Write the brief | Describe one job, its baseline and the decision owner.
2. Review the checks | Set a status, owner, review date and evidence for each item.
3. Record tests | Save expected and observed results before choosing Pass.
4. Test the business case | Enter your own inputs in Cost planner. Zero and blank mean different things.
5. Complete the handover | Record access, recovery and ongoing responsibility.
Phase | Checks | Ready with a record | Blocked | Excluded with reason
Business case | 6 | 0 | 0 | 0
Scope | 6 | 0 | 0 | 0
Test | 6 | 0 | 0 | 0
Handover | 6 | 0 | 0 | 0
Total | 24 | 0 | 0 | 0
Ready/excluded records needing detail | 0
Test results
Pass with recorded evidence | 0 |  | Failed tests | 0
Cost planner result
Net capacity value per month |  |  | Currency | USD
Capacity-value payback (months)
Yellow cells are editable. White and blue-grey cells contain guidance or formulas.
Ready is your recorded judgement. Counts show documented reviews, not certification or a launch approval.
Freed hours are capacity. They become cash savings only if an actual expense changes.

## Project brief
Project brief
Write the decisions that the build, tests and handover must follow.
Question | Your project | Fictional example: order intake
Project name |  | Draft order intake
Business and process owner |  | Sample Supply. Operations manager.
One job and finished outcome |  | An order email becomes a reviewed CRM draft.
Users and affected people |  | Order coordinator, account manager and customers.
Current process and alternatives |  | Compare a required web form with email extraction.
Baseline period and source |  | Four weeks of inbox records and timed order handling.
Primary metric and target |  | Reduce handling time while checking correction rates.
Review date and decision owner |  | Operations manager reviews the pilot after four weeks.
Pilot boundaries |  | One product category, one inbox, draft-only output.
Deliverables and exclusions |  | One CRM connection; no automatic pricing or customer email.
Data sources and account owners |  | Orders inbox and CRM, access approved by operations.
Sensitive fields and retention |  | Payment details excluded. Agree retention before pilot.
Actions needing human approval |  | Account manager approves price exceptions and sending.
Providers, licences and running costs |  | Model API, workflow host and CRM listed separately.
Dependencies and access still needed |  | A test CRM account and representative sample messages.
Human escalation and fallback |  | Duty manager receives source email, draft and reason.
Unacceptable outcomes / stop conditions |  | Do not invent quantities or send unapproved quotes.
What happens after launch |  | Assign an operator, support cover and retest triggers.
Source references
Resource and workbook publisher | https://benian.ai/resources/ai-project-checklist
Benian Technologies. Worksheet version 2.0, published September 7, 2026.
NIST AI RMF Playbook: Map | https://airc.nist.gov/airmf-resources/playbook/map/
Further guidance on intended use, context, alternatives and affected people. The Playbook is voluntary guidance based on AI RMF 1.0, not a certification checklist.
NIST AI RMF Playbook: Measure | https://airc.nist.gov/airmf-resources/playbook/measure/
Further guidance on relevant evaluation methods, documented tests, performance limits and assessment over time.
NIST AI RMF Playbook: Manage | https://airc.nist.gov/airmf-resources/playbook/manage/
Further guidance on risk response, third-party dependencies, monitoring, contingency and deactivation.
Benian measurement notes | https://benian.ai/case-studies#methodology
How published results distinguish measured, client-reported and projected figures. Checklist examples are illustrative, not client results.
Examples are fictional and are not client results. NIST materials are voluntary further guidance, not a certification.

## Checklist
Checklist
Use Ready after reviewing the evidence. Explain exclusions. Keep open actions visible.
Check ID | Phase | Check | Status | Owner | Review date | Evidence / reference | Open questions / next action | Evidence to request | Record check
one-job | Business case | Define one job clearly | Not started |  |  |  |  | A workflow naming the trigger, inputs, finished output, users and steps a person will keep. | Open
baseline | Business case | Measure the starting point | Not started |  |  |  |  | Dated records of volume, handling time, error or rework rate, and the period and sample used. | Open
success-target | Business case | Set an outcome and a review date | Not started |  |  |  |  | One primary metric, its definition, an agreed target, a review date and a person responsible for checking it. | Open
simpler-alternative | Business case | Compare a simpler alternative | Not started |  |  |  |  | A short comparison of the current process, a simpler change and the proposed AI approach, including costs and limits. | Open
value-and-cost | Business case | Separate capacity value from cash savings | Not started |  |  |  |  | An editable estimate of net hours freed, how those hours will be used, running costs and one-time costs, with assumptions identified. | Open
people-and-impact | Business case | Include the people affected | Not started |  |  |  |  | Input from operators and an accountable owner, with affected customers, sensitive decisions and a route to raise concerns recorded. | Open
written-scope | Scope | Put the deliverables in writing | Not started |  |  |  |  | Deliverables, exclusions, dependencies, milestones, acceptance criteria, price and a written change process. | Open
data-access | Scope | Map the data and account access | Not started |  |  |  |  | A source and account inventory covering access approvers, data quality, sensitive fields, retention and deletion requirements. | Open
action-boundaries | Scope | Define what needs approval | Not started |  |  |  |  | A list of permitted actions, actions requiring approval, prohibited actions and the identity under which changes are made. | Open
integration-contract | Scope | Specify every connection | Not started |  |  |  |  | For each connection: supported API or integration, field mapping, source of truth, identifiers, limits and failure behavior. | Open
supplier-dependencies | Scope | List outside services and limits | Not started |  |  |  |  | Provider and licence inventory with billing owner, usage limits, data terms, version dependencies and replacement options. | Open
pilot-plan | Scope | Plan a limited first release | Not started |  |  |  |  | A pilot population, start and end dates, review checkpoints, release decision owner, and a fallback to the current process. | Open
real-examples | Test | Test representative examples | Not started |  |  |  |  | A test set of routine, incomplete, ambiguous and out-of-scope inputs, with expected outcomes and important cases grouped separately. | Open
quality-thresholds | Test | Record expected and observed results | Not started |  |  |  |  | A test log with expected and observed outcomes, pass criteria, environment or version, reviewer, date and evidence links. | Open
running-limits | Test | Check speed and running costs | Not started |  |  |  |  | Observed response times, usage and cost for ordinary and busy periods, with the test workload and agreed limits documented. | Open
failure-recovery | Test | Try the failure and recovery paths | Not started |  |  |  |  | Tests for timeouts, unavailable services, duplicate requests and restarts, showing retained context and recovery outcomes. | Open
human-handoff | Test | Rehearse the human handoff | Not started |  |  |  |  | A tested escalation trigger, recipient, context package, acknowledgement process and fallback when that person is unavailable. | Open
permissions-and-misuse | Test | Test boundaries and misuse | Not started |  |  |  |  | Tests of denied access, sensitive-data requests, misleading instructions in inputs and actions outside the agreed permissions. | Open
ownership | Handover | Confirm access and ownership | Not started |  |  |  |  | Written terms covering custom deliverables, source access, account control, payment conditions and pre-existing or licensed components. | Open
outcome-records | Handover | Keep a record of outcomes | Not started |  |  |  |  | Dated records, metric definitions, data source, measurement window and a label distinguishing measured results, reports and estimates. | Open
operating-notes | Handover | Get the operating instructions | Not started |  |  |  |  | A runbook and walkthrough covering configuration, version history, monitoring, routine changes, credentials management and common exceptions. | Open
recovery-and-exit | Handover | Rehearse recovery and exit | Not started |  |  |  |  | A tested backup or export, restore steps, pause or shutdown procedure, rollback decision owner and list of dependencies required elsewhere. | Open
support-owner | Handover | Name the owner after launch | Not started |  |  |  |  | Named operating and support owners, coverage and response expectations, incident contact, escalation route, scope and ongoing costs. | Open
review-and-retest | Handover | Schedule review and retesting | Not started |  |  |  |  | A review schedule, retest triggers, unresolved issues with owners, accepted limitations and a recorded launch or continuation decision. | Open
Ready requires an owner, numeric review date and evidence reference. Not applicable requires a reason in Evidence / reference.

## Test log
Test log
Record expected and observed results. Retain failed tests and use a new row for each retest.
Test ID | Check ID | Scenario / conditions | Input / test record | Expected outcome | Observed outcome | Result | Reviewer | Test date | Evidence / issue link | Retest date | Record check
T01 | [5 empty] | Not run |  |  |  |  | Not run
T02 | [5 empty] | Not run |  |  |  |  | Not run
T03 | [5 empty] | Not run |  |  |  |  | Not run
T04 | [5 empty] | Not run |  |  |  |  | Not run
T05 | [5 empty] | Not run |  |  |  |  | Not run
T06 | [5 empty] | Not run |  |  |  |  | Not run
T07 | [5 empty] | Not run |  |  |  |  | Not run
T08 | [5 empty] | Not run |  |  |  |  | Not run
T09 | [5 empty] | Not run |  |  |  |  | Not run
T10 | [5 empty] | Not run |  |  |  |  | Not run
T11 | [5 empty] | Not run |  |  |  |  | Not run
T12 | [5 empty] | Not run |  |  |  |  | Not run
T13 | [5 empty] | Not run |  |  |  |  | Not run
T14 | [5 empty] | Not run |  |  |  |  | Not run
T15 | [5 empty] | Not run |  |  |  |  | Not run
T16 | [5 empty] | Not run |  |  |  |  | Not run
T17 | [5 empty] | Not run |  |  |  |  | Not run
T18 | [5 empty] | Not run |  |  |  |  | Not run
T19 | [5 empty] | Not run |  |  |  |  | Not run
T20 | [5 empty] | Not run |  |  |  |  | Not run
Link tests to checklist IDs. Example scenarios are guidance on the resource page; these test rows contain no example results.

## Cost planner
Cost planner
Monthly capacity model. Enter your own measured or clearly identified estimated inputs.
Currency (use one throughout) | USD |  | Fictional example only | USD
Input | Your value | Definition / source to record | Example input | Example value | Example assumption
Eligible jobs per month |  | Use the same population and month basis throughout. | Eligible jobs per month | 400 | 400 order emails per month.
Current human minutes per job |  | Include correction and follow-up time in the baseline. | Current human minutes per job | 12 | 12 minutes of handling before the system.
Human minutes per system job |  | Include review, corrections and remaining manual work. | Human minutes per system job | 4 | 4 minutes of review and correction afterward.
Share of jobs using the system |  | Enter 0%–100%; exclude work that stays entirely manual. | Share of jobs using the system | 75% | 75% of eligible order emails use the system.
Loaded labor value per hour |  | Planning value of freed capacity, not an assumed cash saving. | Loaded labor value per hour | 35 | 35 currency units per hour of capacity.
Fixed running cost per month |  | Hosting, subscriptions and support fees paid every month. | Fixed running cost per month | 120 | 120 for subscriptions and hosting.
Variable cost per system job |  | Model/API usage or other incremental cost per processed job. | Variable cost per system job | 0.08 | 0.08 per processed email.
Oversight hours per month |  | Additional internal maintenance time; deducted from capacity. | Oversight hours per month | 4 | 4 hours of internal oversight per month.
Other running cost per month |  | Additional recurring cash cost; do not double-count fixed fees. | Other running cost per month | 40 | 40 of other recurring costs.
One-time external build cost |  | Quoted implementation and other one-time external costs. | One-time external build cost | 4000 | 4000 external build cost.
One-time internal setup hours |  | Your team’s setup, testing and training time. | One-time internal setup hours | 12 | 12 hours of internal setup work.
Loaded setup labor value per hour |  | Value internal setup consistently with your business case. | Loaded setup labor value per hour | 35 | 35 per internal setup hour.
Enter 0 for a real zero. Blank inputs leave dependent results blank. |  |  | These numbers are fictional. They do not feed your results.
Calculation | Your result | How it is calculated | Example calculation | Example result | How it is calculated
System jobs per month |  | Eligible jobs × share using the system. | System jobs per month | 300 | Eligible jobs × share using the system.
Net hours freed per month |  | Time difference × system jobs ÷ 60, less oversight. | Net hours freed per month | 36 | Time difference × system jobs ÷ 60, less oversight.
Gross capacity value per month |  | Net hours freed × loaded labor value. | Gross capacity value per month | 1260 | Net hours freed × loaded labor value.
Running cost per month |  | Fixed + variable cost × system jobs + other recurring cost. | Running cost per month | 184 | Fixed + variable cost × system jobs + other recurring cost.
Net capacity value per month |  | Gross capacity value less running cost. | Net capacity value per month | 1076 | Gross capacity value less running cost.
Total one-time investment |  | External build cost + internal setup hours × hourly value. | Total one-time investment | 4420 | External build cost + internal setup hours × hourly value.
Capacity-value payback (months) |  | One-time investment ÷ positive net monthly capacity value. | Capacity-value payback (months) | 4.1078 | One-time investment ÷ positive net monthly capacity value.
Interpret the result
Capacity value is not revenue, profit or cash saved. Decide how the freed time will actually be used.
The model assumes a steady month. It excludes ramp-up, tax, financing, inflation and speculative additional sales.
Negative net capacity means this set of inputs does not recover its running cost on a capacity-value basis.
Payback is n.a. when net monthly capacity value is zero or negative. It is not a guarantee of return.
Retest with lower adoption, more review time and higher running costs. Replace estimates with pilot records.

## Handover
Handover
Record locations and responsible people. Keep passwords and API keys in your approved password manager.
Item | Location / evidence / decision | Responsible owner | Status | Verified date | Open action / next review
Custom code / workflow exports |  |  | Not started
Account ownership and billing |  |  | Not started
Licences and dependency inventory |  |  | Not started
Data locations and retention rules |  |  | Not started
Approved configuration / version |  |  | Not started
Operating runbook and walkthrough |  |  | Not started
Monitoring and outcome definitions |  |  | Not started
Human escalation and cover |  |  | Not started
Backup and restore evidence |  |  | Not started
Pause, rollback and shutdown steps |  |  | Not started
Open issues and accepted limitations |  |  | Not started
Support scope and response expectations |  |  | Not started
Training / operator walkthrough |  |  | Not started
Retest schedule and triggers |  |  | Not started
Continuation decision
Decision owner and date
Conditions / next review